## Plan1
Feature	Priority	Value	Difficulty	Rank
JDBC DataSource Access	E	L	S	49	50
Injection	E	L	M	47	90
Application Service/Modules	E	L	M	47	50
Validation	E	M	S	47	90
Environment Integration - Application Server	E	M	M	45	0
Transaction Support	E	L	L	45	0
Data Store	E	L	L	45	10
UI for Web	E	L	L	45	0
Bootstrap	E	M	L	43	90
Services	E	M	L	43	90
Quantity	E	S	M	43	100
Sequences	E	S	M	43	90
Logging	E	S	M	43	100
Managed I/O	E	M	L	43	90
Work Scheduling	V	L	M	32	40
Domain Model Support	V	L	L	30	0
UI for Desktop (Swing)	V	L	L	30	0
Authentication and Authorization Control	V	L	L	30	0
Addressing	V	M	M	30	100
Work Unit Processing	V	M	L	28	0
Environment Integration - Standalone	V	M	L	28	0
Notifications	V	S	M	28	0
Atlas	V	S	M	28	100
License Control	V	S	L	26	90
Dynamic Service Loading	V	S	L	26	90
User Control: JAAS integration	V	S	L	26	0
Email Sending	X	L	S	19	100
Reports Support	X	L	S	19	90
Chart Support	X	L	M	17	90
Email Receiving	X	M	S	17	0
Easy Cryptography Support	X	M	M	15	0
UI for Testing	X	M	M	15	0
UI for Ajax	X	M	M	15	0
Tags for UI for Web	X	M	L	13	0
Environent Integration - Web Container Only	X	M	L	13	0
Document Search	X	S	L	11	0
Geographic Maps integration	X	S	L	11	0
UI for SWT	X	S	L	11	0
Webservice Consuming : SOAP	X	S	L	11	0
Webservice Providing : SOAP	X	S	L	11	0
Webservice Consuming : REST	X	S	L	11	0
Webservice Providing : REST	X	S	L	11	0

## Plan2
3 de Outubro de 2008
Feature	Value	Priority	Difficulty	Effort	Net Value	Rank	Progress(%)	Notes
Bootstrap	L	X	S	L	3	8	90	Revise
Quantity	M	X	S	L	1	6	100
Services	L	X	M	L	2	6	90
Logging	L	X	L	S	0	6	100
JDBC DataSource Access	L	X	L	S	0	6	50
Transaction Support	L	X	M	L	2	6	5
Sequences	S	X	M	S	-1	5	90	Integrate to native sequence from jdbc
Data store	L	X	L	L	0	4	60
Managed I/O	M	X	L	M	-2	3	100
Work Unit Processing	L	M	S	M	3	3	90
UI for Web	L	L	M	L	2	2	0
Injection	M	X	L	L	-2	2	90	Integrate with the core reflection abilities
Notifications	M	L	M	S	0	2	90
Authentication and Authorization Control	L	M	M	M	2	1	50
Environment Integration - Application Server	S	L	M	S	-1	1	0
Domain Model Support	L	L	L	L	0	0	50
Application Modules	M	L	M	L	0	0	50
Email Sending	M	M	M	S	0	0	100
Email Receiving	S	S	S	M	0	-1	0
Validation	M	L	L	M	-2	-1	90	Instance validador base on annotations
Environent Integration - Web Container Only	M	L	L	M	-2	-1	0
Work Scheduling (Alarm Clock)	S	M	M	M	-1	-2	90
Reports Support	S	M	M	M	-1	-2	100
UI for Testing	L	S	L	M	0	-2	0
License Control	L	S	L	M	0	-2	90
Atlas	S	S	M	M	-1	-3	90	use XML DataStore. Reprocess files to xml
Environment Integration - Standalone	S	L	L	L	-3	-3	20
Addressing	S	S	M	M	-1	-3	90
UI for Ajax	M	S	M	L	0	-3	0
Tags for UI for Web	M	S	M	L	0	-3	0
Easy Cryptography Support	M	S	L	S	-2	-3	0
Webservice Providing : SOAP	S	S	M	L	-1	-4	0
Webservice Providing : REST	S	S	M	L	-1	-4	0
UI for Desktop (Swing)	L	L	L	X	0	-4	10
Dynamic Service Loading	M	M	L	L	-2	-4	90
Chart Support	S	M	L	M	-3	-4	90
User Control: JAAS integration	S	M	L	L	-3	-5	0
Webservice Consuming : SOAP	S	S	X	L	-7	-8	0
Webservice Consuming : REST	S	S	X	L	-7	-8	0
Geographic Maps integration	S	S	L	X	-3	-10	0
Document Search	S	S	L	X	-3	-10	0
UI for SWT	M	S	X	X	-6	-11	0