## Plan2
3 de Outubro de 2008
Feature	Value	Priority	Difficulty	Effort	Net Value	Rank	Progress(%)	Notes
Bootstrap	L	X	S	L	#NOME?	#NOME?	90	Revise
Quantity	M	X	S	L	#NOME?	#NOME?	100
Services	L	X	M	L	#NOME?	#NOME?	90
Logging	L	X	L	S	#NOME?	#NOME?	100
JDBC DataSource Access	L	X	L	S	#NOME?	#NOME?	90
Transaction Support	L	X	M	L	#NOME?	#NOME?	5
Sequences	S	X	M	S	#NOME?	#NOME?	90	Integrate to native sequence from jdbc
Data store	L	X	L	L	#NOME?	#NOME?	60
Managed I/O	M	X	L	M	#NOME?	#NOME?	100
Work Unit Processing	L	M	S	M	#NOME?	#NOME?	90
UI for Web	L	L	M	L	#NOME?	#NOME?	0
Injection	M	X	L	L	#NOME?	#NOME?	90	Integrate with the core reflection abilities
Notifications	M	L	M	S	#NOME?	#NOME?	90
Authentication and Authorization Control	L	M	M	M	#NOME?	#NOME?	50
Environment Integration - Application Server	S	L	M	S	#NOME?	#NOME?	0
Domain Model Support	L	L	L	L	#NOME?	#NOME?	50
Application Modules	M	L	M	L	#NOME?	#NOME?	50
Email Sending	M	M	M	S	#NOME?	#NOME?	100
Email Receiving	S	S	S	M	#NOME?	#NOME?	0
Validation	M	L	L	M	#NOME?	#NOME?	90	Instance validador base on annotations
Environent Integration - Web Container Only	M	L	L	M	#NOME?	#NOME?	0
Work Scheduling (Alarm Clock)	S	M	M	M	#NOME?	#NOME?	90
Reports Support	S	M	M	M	#NOME?	#NOME?	100
UI for Testing	L	S	L	M	#NOME?	#NOME?	0
License Control	L	S	L	M	#NOME?	#NOME?	90
Atlas	S	S	M	M	#NOME?	#NOME?	90	use XML DataStore. Reprocess files to xml
Environment Integration - Standalone	S	L	L	L	#NOME?	#NOME?	20
Addressing	S	S	M	M	#NOME?	#NOME?	90
UI for Ajax	M	S	M	L	#NOME?	#NOME?	0
Tags for UI for Web	M	S	M	L	#NOME?	#NOME?	0
Easy Cryptography Support	M	S	L	S	#NOME?	#NOME?	0
Webservice Providing : SOAP	S	S	M	L	#NOME?	#NOME?	0
Webservice Providing : REST	S	S	M	L	#NOME?	#NOME?	0
UI for Desktop (Swing)	L	L	L	X	#NOME?	#NOME?	10
Dynamic Service Loading	M	M	L	L	#NOME?	#NOME?	90
Chart Support	S	M	L	M	#NOME?	#NOME?	90
User Control: JAAS integration	S	M	L	L	#NOME?	#NOME?	0
Webservice Consuming : SOAP	S	S	X	L	#NOME?	#NOME?	0
Webservice Consuming : REST	S	S	X	L	#NOME?	#NOME?	0
Geographic Maps integration	S	S	L	X	#NOME?	#NOME?	0
Document Search	S	S	L	X	#NOME?	#NOME?	0
UI for SWT	M	S	X	X	#NOME?	#NOME?	0
DDL Scripting					20
UIComponent Interface Hierarchy					10
UIModel models					10
Phone Number					0
Atlas data to storage					0
Task toolbox					0
Webservice publisher					0
Improve Injection					80
Improve Bootstrap					80
Storages must handle Quantity and Measure					0
Native Dialect Sequences					100
Annotation based Validator					0
Transations					0
JNDI Datasource					100
Image Service					0
Login Autentication					0
UILayouts